## Project Tracker
Project & Operations Tracker — FY 2025
Project Name | Owner | Department | Phase | Start Date | Due Date | % Complete | Status | Budget ($) | Spent ($) | Variance ($) | Notes
CRM Migration | Sarah Chen | IT | Execution | 2025-01-06 | 2025-06-30 | 58% | On Track | 450000 | 261000 | 189000 | Phase 2 kick-off complete
Brand Refresh | Mike Torres | Marketing | Planning | 2025-02-03 | 2025-05-31 | 25% | On Track | 120000 | 30000 | 90000 | Agency brief approved
ERP Upgrade | Lisa Park | Finance | Discovery | 2025-01-13 | 2025-09-30 | 10% | At Risk | 980000 | 98000 | 882000 | Vendor selection delayed
Hiring — Eng (×12) | Tom Reed | HR | Execution | 2025-01-06 | 2025-07-31 | 67% | On Track | 240000 | 160800 | 79200 | 8 of 12 roles filled
Salesforce CPQ | Amy Johnson | Sales Ops | Testing | 2024-11-04 | 2025-04-30 | 85% | On Track | 310000 | 263500 | 46500 | UAT sign-off pending
Data Warehouse v2 | Carlos Ruiz | Engineering | Execution | 2025-01-20 | 2025-08-31 | 40% | On Track | 620000 | 248000 | 372000 | Snowflake migration in progress
Office Expansion | Dana White | Facilities | Planning | 2025-03-03 | 2025-12-31 | 8% | On Track | 750000 | 60000 | 690000 | Permits submitted
SOC 2 Certification | James Lee | Security | Execution | 2025-01-06 | 2025-07-15 | 55% | On Track | 180000 | 99000 | 81000 | Audit fieldwork started
Mobile App — v3 | Priya Patel | Product | Build | 2025-02-03 | 2025-08-31 | 30% | At Risk | 540000 | 162000 | 378000 | Backend API blocked
Partner Portal | Ryan Kim | Engineering | Design | 2025-03-03 | 2025-10-31 | 15% | On Track | 280000 | 42000 | 238000 | UX wireframes in review
GDPR Remediation | Elena Vasquez | Legal | Execution | 2025-01-13 | 2025-05-31 | 70% | On Track | 95000 | 66500 | 28500 | DPA updates complete
Supply Chain Audit | Ben Foster | Operations | Complete | 2025-01-06 | 2025-03-31 | 100% | Complete | 160000 | 148000 | 12000 | Report delivered
Content Platform | Sophie Grant | Marketing | Discovery | 2025-04-01 | 2025-11-30 | 5% | Not Started | 210000 | 10500 | 199500 | Kick-off scheduled Apr 14
BI Dashboard Rollout | Derek Nguyen | Analytics | Execution | 2025-02-10 | 2025-06-30 | 45% | On Track | 135000 | 60750 | 74250 | Exec dashboard live
Customer Success Tool | Mia Thornton | CS | At Risk | 2025-01-20 | 2025-05-31 | 35% | At Risk | 175000 | 61250 | 113750 | Integration partner issues
TOTALS | [7 empty] | 5245000 | 1771300 | 3473700

## Milestones
Key Milestones — Q1–Q2 2025
Milestone | Project | Owner | Target Date | Actual Date | Status | Notes
CRM Phase 1 Go-Live | CRM Migration | Sarah Chen | 2025-02-28 | 2025-02-26 | Complete | Two days early
Brand Concept Approval | Brand Refresh | Mike Torres | 2025-03-15 |  | On Track
ERP Vendor Selected | ERP Upgrade | Lisa Park | 2025-03-31 |  | At Risk | Delayed by 3 weeks
Q1 Hiring Goal (6 roles) | Hiring — Eng (×12) | Tom Reed | 2025-03-31 | 2025-03-28 | Complete
CPQ UAT Sign-Off | Salesforce CPQ | Amy Johnson | 2025-04-15 |  | On Track
DWH Dev Complete | Data Warehouse v2 | Carlos Ruiz | 2025-05-31 |  | On Track
SOC 2 Audit Complete | SOC 2 Certification | James Lee | 2025-06-01 |  | On Track
Mobile Beta Release | Mobile App — v3 | Priya Patel | 2025-05-15 |  | At Risk | API blocker risk
GDPR Remediation Done | GDPR Remediation | Elena Vasquez | 2025-05-31 |  | On Track
Supply Chain Report | Supply Chain Audit | Ben Foster | 2025-03-31 | 2025-03-28 | Complete | Report delivered early